## Feuil1
ETU001844 | RAMANANTSALAMA Dirk Tony
Catégorie | Taches | Type | Qui | Estimation | Temps passé | Reste à faire | Avancement
Database Migration | create_marque | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_type_ram | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_type_ecran | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_type_clavier | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_ram_ref_laptop | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_type_processeur | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_type_carte_graphique | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_reference_laptop | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_laptop | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_point_vente | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_entree_stock | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_sortie_stock | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_entree_stock_point_vente | SQL | Tony | 5 |  | 5 | 0%
Database Migration | create_sortie_stock_point_vente | SQL | Tony | 5 |  | 5 | 0%
Frontend Magasin | List Ref LapTop | Svelte | Tony | 10 |  | 10 | 0%
Frontend Magasin | Upsert Ref Laptop | Svelte | Tony | 10 |  | 10 | 0%
Frontend Magasin | Remove Ref LapTop | Svelte | Tony | 10 |  | 10 | 0%
Frontend Magasin | List Laptop | Svelte | Tony | 10 |  | 10 | 0%
Frontend Magasin | Upsert LapTop | Svelte | Tony | 10 |  | 10 | 0%
Frontend Magasin | Remove LapTop | Svelte | Tony | 10 |  | 10 | 0%
Frontend Magasin | Insert LapTop to Stock | Svelte | Tony | 10 |  | 10 | 0%
Frontend Magasin | Transfert Laptop to PV Stock | Svelte | Tony | 10 |  | 10 | 0%
Frontend Point De Vente | List LapTop Recues | Svelte | Tony | 10 |  | 10 | 0%
Frontend Point De Vente | Rececption Validation | Svelte | Tony | 10 |  | 10 | 0%
Frontend Point De Vente | Renvoi de Laptop | Svelte | Tony | 10 |  | 10 | 0%
Frontend Point De Vente | Vente de Laptop | Svelte | Tony | 10 |  | 10 | 0%
Backend Setup | DB Connection Setup | Rust | Tony | 5 |  | 5 | 0%
Backend Setup | Actix Server state setup | Rust | Tony | 5 |  | 5 | 0%
Backend Setup | Actix Server Setup | Rust | Tony | 5 |  | 5 | 0%
Backend Setup | Magasin GraphQL setup | Rust | Tony | 5 |  | 5 | 0%
Backend Setup | Point de Vente GraphQL Setup | Rust | Tony | 5 |  | 5 | 0%
FrontendCodeGen | Magasin GraphQL Codegen | Typescript | Tony | 10 |  | 10 | 0%
FrontendCodeGen | Point de Vente GraphQL Codegen | Typescript | Tony | 10 |  | 10 | 0%
Database Migration | create_v_laptop | SQL | Tony | 10 |  | 10 | 0%
Rust Models | Model V_Laptop | Rust | Tony | 2 |  | 2 | 0%
Database Migration | create_v_ram | SQL | Tony | 5 |  | 5 | 0%
Rust Models | Modele Vram | Rust | Tony | 2 |  | 2 | 0%
Backend Magasin | List laptops | Rust | Tony | 2 |  | 2 | 0%
Backend Magasin | Upsert laptops | Rust | Tony | 2 |  | 2 | 0%
Backend Magasin | Upsert Ref Laptop | Rust | Tony | 2 |  | 2 | 0%
Rust Models | Modele EntreeStock | Rust | Tony | 2 |  | 2 | 0%
Backend Magasin | Insert Entree Stock | Rust | Tony | 2 |  | 2 | 0%
Rust Models | Model Sortie Stock | Rust | Tony | 2 |  | 2 | 0%
Rust Models | Model Point_vente | Rust | Tony | 2 |  | 2 | 0%
Rust Models | Model EntreeStockPointVente | Rust | Tony | 2 |  | 2 | 0%
Rust Models | Insert EntreeStockPointVente | Rust | Tony | 2 |  | 2 | 0%
Backend Point Vente | Validate transfert | Rust | Tony | 10 |  | 10 | 0%
Rust Models | Model Sortie Stock Point Vente | Rust | Tony | 10 |  | 10 | 0%
Rust Models | Insert Sortie Stock Point Vente | Rust | Tony | 10 |  | 10 | 0%
Backend Point Vente | Vente de Laptop | Rust | Tony | 10 |  | 10 | 0%
Database Migration | alter_entree_stock_renvoie | SQL | Tony | 10 |  | 10 | 0%
Database Migration | create_v_stock | SQL | Tony | 10 |  | 10 | 0%
Backend Point Vente | Renvoi de Laptop | Rust | Tony | 10 |  | 10 | 0%
Backend Magasin | Validation renvoi laptop | Rust | Tony | 10 |  | 10 | 0%
Integration Magasin | List Ref LapTop | Typescript | Tony | 5 |  | 5 | 0%
Integration Magasin | Upsert Ref Laptop | Typescript | Tony | 5 |  | 5 | 0%
Integration Magasin | Remove Ref LapTop | Typescript | Tony | 5 |  | 5 | 0%
Integration Magasin | List Laptop | Typescript | Tony | 5 |  | 5 | 0%
Integration Magasin | Upsert LapTop | Typescript | Tony | 5 |  | 5 | 0%
Integration Magasin | Remove LapTop | Typescript | Tony | 5 |  | 5 | 0%
Integration Magasin | Insert LapTop to Stock | Typescript | Tony | 5 |  | 5 | 0%
Integration Magasin | Transfert Laptop to PV Stock | Typescript | Tony | 5 |  | 5 | 0%
Integration Point De Vente | List LapTop Recues | Typescript | Tony | 5 |  | 5 | 0%
Integration Point De Vente | Rececption Validation | Typescript | Tony | 5 |  | 5 | 0%
Integration Point De Vente | Renvoi de Laptop | Typescript | Tony | 5 |  | 5 | 0%
Integration Point De Vente | Vente de Laptop | Typescript | Tony | 5 |  | 5 | 0%
|  |  |  | 412 | 0 | 412 | 0%
*Valeur en Minutes
Estimation: | 412
Temps passé | 0
Reste à faire | 412
par défaut : Reste à faire = Estimation - Temps Passé

## Feuille2
*Valeur en Minutes
Estimation: | ny fotoana nieritreretana hahavitana azy
Temps passé | ny fotoana efa lany
Reste à faire | ny fotoana sisa (rehefa 0 io dia efa vita zany)
par défaut : Reste à faire = Estimation - Temps Passé